BUDGET ADDENDUM

EMO Oregon Day Center Client Management System

January 22, 2026

Note: This addendum contains budget details and is provided separately from the Statement of Work for discretionary distribution. Rates shown are preliminary and subject to discussion.

# Budget Summary

| Item | Amount |
| --- | --- |
| Total Estimated Project Cost | $4,500.00 |
| Contingency Reserve (Recommended) | $500.00 |
| Total Budget Recommendation | $5,000.00 |

# Itemized Cost Breakdown

| Task | Hours | Rate | Extended |
| --- | --- | --- | --- |
| Phase 1: Discovery & requirements | 4 | $75.00 | $300.00 |
| Phase 2: Backend development | 16 | $75.00 | $1,200.00 |
| Phase 2: Frontend development | 12 | $75.00 | $900.00 |
| Phase 3: Data migration | 4 | $75.00 | $300.00 |
| Phase 3: Testing & security hardening | 8 | $75.00 | $600.00 |
| Phase 3: Documentation | 8 | $75.00 | $600.00 |
| Phase 4: Deployment & training | 8 | $75.00 | $600.00 |
| Subtotal | 60 |  | $4,500.00 |

# Rate Notes

The base rate of $75/hour reflects nonprofit pricing for a mission-aligned project. This rate assumes:

- Payment terms of Net 15 or milestone-based payments

- Scope limited to deliverables outlined in the Statement of Work

- Remote work with on-site visits only as needed for deployment/training

- No ongoing maintenance contract (available separately if desired)

Rate flexibility: Open to discussion based on payment structure, timeline, or scope adjustments.

# Contingency Reserve

The $500 contingency (approximately 11%) covers:

- Unexpected complexity in Excel data migration

- Additional reporting requirements discovered during discovery

- Minor hardware needs (USB backup drive, surge protector)

- Additional training sessions if needed

Unused contingency is not billed. Any contingency use will be documented and approved before incurring.

# Alternative Engagement Structures

| Structure | Description |
| --- | --- |
| Fixed Price | $5,000 fixed fee for complete delivery; overrun risk absorbed by consultant |
| Time & Materials | Hourly billing at $75/hr with not-to-exceed cap; flexibility for scope changes |
| Milestone-Based | Payment tied to phase completion (e.g., 25% discovery, 50% prototype, 25% go-live) |

# Exclusions

Not included (quoted separately if needed):

- Hardware procurement

- Ongoing maintenance and support beyond deployment

- Integration with external systems (HMIS, etc.)

- Network infrastructure changes

- Cloud hosting or offsite backup services

# Contact

Consultant: Aaron Johnson (AJ)

Independent Technical Consultant

Referred via: Express Employment Professionals

Document Control: Version 1.0 (DRAFT). Final budget confirmed after discovery session.